## Sheet1
SL# | Module | Sub-Module | Finding Issue/Development | Assigned Person | Status | Remarks
1 | HR | Basic | Add field Skype Id | Mr. Tonoy
2 |  | Promotion | Add field Old designation and new designation | Mr. Tonoy
3 |  | File Attachment | Add File Upload option for any kind of Option | Mr. Tonoy
4 |  | Leave | Leave Cancel Window | Mr. Tonoy
5 |  | Leave | Leave status | Mr. Tonoy
6 |  | Leave | Manual leave apply | Mr. Tonoy
7 |  | Leave | On Leave Employee | Mr. Tonoy
8 |  | ESS | In ESS Portal View only logged in persons profile | Mr. Tonoy
9 |  | ESS | View Attendance | Mr. Tonoy
10 |  | Attendance | Update Attendance | Mr. Tonoy
11 |  | Attendance | Approve Attendance | Mr. Tonoy
12 | Payroll | Bonus | Festival Bonus Process | Mr. Ruhul | On Going
13 |  | Bonus | Prorated Festival Bonus Process | Mr. Ruhul | On Going
14 |  | Final Settlement | Report | Mr. Azmal | On Going
15 |  | Tax | Tax Calculation Report | Mr. Ruhul | On Going
16 |  | Tax | Final Tax Certificate Report | Mr. Azmal | On Going
17 |  | PF | PF Advance Repay | Mr. Ruhul
18 |  | PF | FDR Schedule | Mr. Bashar
19 |  | Emailing | Email Payslip | Mr. Ruhul
20 |  | Emailing | Email Taxcard | Mr. Bashar
21 |  | Emailing | Email Investment | Mr. Azmal